## project
GANTT CHART
[8 empty] | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [6 empty] | % Complete (beyond plan)
[8 empty] | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [6 empty] | % Complete (beyond plan)
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | WEEKLY PERIOD
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Introduction and Research
| Brief | 1 | 1 | 1 | 1 | 100%
| Initial Research | 2 | 2 | 2 | 2 | 100%
| Discussion | 3 | 2 | 3 | 2 | 100%
| Iteration of Concept | 4 | 1 | 4 | 1 | 100%
Conceptual Design
| Initial Sketching | 4 | 2 | 4 | 2 | 100%
| SiteMap | 4 | 2 | 4 | 2 | 100%
| Data flow Diagram | 5 | 2 | 5 | 2 | 100%
| Interface Design | 5 | 2 | 5 | 2 | 100%
Development
| Research on Web technologies | 6 | 2 | 6 | 2 | 100%
| Front-End Developement | 8 | 2 | 8 | 2 | 100%
| Data Base Design | 9 | 1 | 9 | 1 | 100%
| Back-End Development | 9 | 3 | 9 | 3 | 100%
| Unit Testing | 9 | 3 | 9 | 3 | 100%
| System Test | 11 | 1 | 11 | 1 | 100%
| Github Submission | 11 | 1 | 11 | 1 | 100%
Submission
| Development Design Document | 11 | 4 | 12 | 4 | 100%
| Video Demo Presentation | 11 | 1 | 11 | 2 | 100%
| Project Submission | 15 | 1 | 15 | 1 | 100%
Implementation
| Research for Hosting Services | 13 | 2 | 15 | 1 | 0%
| Deployment | 13 | 2 | 16 | 1 | 0%
| Implementation Test | 15 | 2 | 17 | 2 | 0%